## Slide 1: Scrum Ceremonies and the Sprint Lifecycle
What a Scrum team actually does and when, and where testing fits in every sprint.
Sprint
Artifacts
User stories
Events
Testing in a sprint
Notes: Delivery models gave a one-slide view of Scrum. This lesson is the full version: what a Scrum team actually does, day by day, and where testing fits.
- Ask: "If a sprint is two weeks, when should testing start?" Most beginners answer "week two". By the end of the lesson the answer is "day one".

## Slide 2: Learning Objectives
1
Explain the sprint, its rules, and the three artifacts with their commitments.
2
Write a user story with Given/When/Then acceptance criteria.
3
Explain story points, velocity and how to read a burndown.
4
Describe the Scrum events and the QE's role in each.
5
Show how testing runs continuously inside a sprint.
2 / 30
Notes: Scrum Guide (2020) wording: the five events are the Sprint itself, Sprint Planning, Daily Scrum, Sprint Review and Sprint Retrospective. Backlog refinement is an ongoing activity, not an event, but we cover it because the QE's work there matters so much.

## Slide 3: The Sprint and Scrum Basics
The framework, sprint rules, artifacts and commitments
01
3 / 30
Notes: Part 1: the container (the sprint) and the things it produces.

## Slide 4: Analogy: The Relay Race
PART 1
Waterfall: a relay
The baton passes from analysts to developers to testers. Testers run only when everyone else has finished; a dropped baton loses the race.
Scrum: run together
The whole team runs short laps (sprints) side by side. After every lap there is a working, tested product in hand.
4 / 30
Notes: This is the deck's one analogy. The QE is not waiting at the last hand-over; they run every lap with the team.
- Use it again on the "Scrum-fall" slide: a sprint where developers code in week one and testers test in week two is a relay squeezed into two weeks.

## Slide 5: The Scrum Framework
PART 1
Product Backlog
(Product Goal)
Sprint Planning
Sprint Backlog
(Sprint Goal)
Sprint
1–4 weeks
Daily Scrum
Increment
(meets DoD)
Sprint Review
Sprint Retrospective
Blue: artifacts · Purple: events · Green: the Increment that meets the Definition of Done
5 / 30
Notes: Walk the picture left to right: the Product Owner orders the Product Backlog; Sprint Planning selects items into the Sprint Backlog with a Sprint Goal; during the sprint the Developers meet daily; the sprint produces an Increment that meets the Definition of Done; Review and Retrospective close the sprint.
- Scrum is a lightweight framework: a few rules and roles, not a detailed method. Teams fill in the practices, such as how they test.

## Slide 6: Sprint Rules
PART 1
Rule | What it means
Timeboxed | One month or less; most teams choose 2 weeks
Fixed length | Every sprint the same length; it ends on its date
Has a goal | One clear Sprint Goal gives the work meaning
No gaps | The next sprint starts as soon as one ends
Goal protected | No changes that endanger the goal; quality never drops
6 / 30
Notes: Why these rules: short cycles give fast feedback and limit how wrong a plan can go; a fixed length makes planning predictable and removes the temptation to "take a few more days".
- Scope can still be clarified and renegotiated with the PO as the team learns.
- A sprint can be cancelled only by the PO, and only if the Sprint Goal becomes obsolete. Two weeks is the most common length.

## Slide 7: A Two-Week Sprint at a Glance
PART 1
D1
D2
D3
D4
D5
D6
D7
D8
D9
D10
Planning ≤4h
Daily Scrum, 15 min every day
Refine
Refine
Review ≤2h
Retro ≤1.5h
Build and test together, story by story
Timeboxes for a 2-week sprint; 1-month maximums: 8h, 4h, 3h
Refinement is an ongoing activity, often 1–2 sessions per sprint.
7 / 30
Notes: Day by day (2-week sprint): Day 1 Sprint Planning; Days 2–8 build and test continuously, Daily Scrum every day, a refinement session around Day 3 and Day 8; mid-sprint check around Day 5 (is the goal still safe?); Day 9 finish remaining tests and regression; Day 10 Sprint Review then Retrospective. The next sprint starts immediately.
- Timeboxes for 2 weeks are typical, not rules: Planning up to 4 hours, Daily Scrum 15 minutes, Review up to 2 hours, Retrospective up to 1.5 hours.

## Slide 8: Artifacts and Commitments
PART 1
Artifact | What it is | Commitment
Product Backlog | Ordered list of everything the product might need; owned by the PO | Product Goal: the long-term objective
Sprint Backlog | Items chosen for this sprint plus a plan; owned by the Developers | Sprint Goal: the one objective for this sprint
Increment | A usable step toward the Product Goal; increments add up | Definition of Done: what "finished" means
8 / 30
Notes: Example Product Goal: "Let first-time shoppers find and buy a product in under three minutes." Example Sprint Goal: "A shopper can add items to a cart and see an accurate total."
- Work becomes part of the Increment only when it meets the Definition of Done. There is no partial credit.

## Slide 9: Definition of Ready and Done
PART 1
Definition of Ready
Is the story clear enough to start?
Work in the sprint
Definition of Done
Is it really finished?
Has acceptance criteria
Estimated
No blocking dependencies
Team practice, not official Scrum
Code reviewed; unit tests pass
Acceptance criteria tested
No open critical or high bugs
Regression passed; PO accepted
9 / 30
Notes: DoR is the front door: a checklist a story passes before it is pulled into a sprint. It is not an official Scrum artifact but is widely used.
DoD is the exit: an official Scrum commitment attached to the Increment.
- A story that is "99 percent done" is not done.
- Do not confuse the DoD (applies to every item) with acceptance criteria (specific to one story).
- QEs often help write and sharpen both checklists.

## Slide 10: Stories, Estimation and Refinement
User stories, Given/When/Then, story points, burndown
02
10 / 30
Notes: Part 2: how work is described, sized and tracked.

## Slide 11: User Stories and INVEST
PART 2
As a [type of user], I want [goal], so that [benefit].
Example: As a shopper, I want to save my address so that I don't retype it.
I
Independent
N
Negotiable
V
Valuable
E
Estimable
S
Small
T
Testable
INVEST: a good story. T is the QE's special lens: if you can't imagine how to test it, it isn't ready.
11 / 30
Notes: A user story is a short description of a feature from the point of view of the person who wants it. It is a placeholder for a conversation, not a full specification.
INVEST: Independent (can be built and tested alone), Negotiable (details are discussed), Valuable (to a user or the business), Estimable (the team can size it), Small (fits in a sprint), Testable (you can describe how to prove it works).

## Slide 12: Acceptance Criteria: Given / When / Then
PART 2
Given
A starting situation: the context or preconditions.
When
Something happens: a user or system action.
Then
An observable result. Every Then must be checkable.
EXAMPLE
Given I am on the login page with a registered account, When I enter a wrong password and click Log in, Then I see "Invalid email or password" and stay on the page.
12 / 30
Notes: A story says what the user wants; acceptance criteria (AC) say how we will know it is correctly done: specific, testable conditions.
- Given/When/Then turns AC directly into test cases. It is the format used later in the course for BDD.
- Tip: write at least one unhappy path (wrong password, empty field) for every story.

## Slide 13: Story Points, Planning Poker, Velocity
PART 2
Story points: relative size, not hours (1, 2, 3, 5, 8, 13…)
Points include testing effort, not only coding
Planning poker: everyone votes privately, reveals at once
Big gaps? Highest and lowest voters explain, then re-vote
Velocity: points completed (meeting DoD) per sprint
Velocity forecasts one team; never compare teams with it
13 / 30
Notes: 8 points is not 8 hours; it is roughly twice as big and uncertain as 4 points. Gaps widen in the scale because large estimates are less precise.
- A QE who votes 8 when developers vote 3 might say "this needs checking on three browsers and two payment types". That is planning poker working well.
- Example velocity: 24, 28 and 26 points in three sprints, so plan about 26 next sprint. Half-done stories count as zero.

## Slide 14: Reading a Burndown Chart
PART 2
Chart: 
| D0 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Ideal | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
Actual | 30 | 30 | 28 | 27 | 27 | 22 | 19 | 17 | 12 | 6 | 0
Actual above ideal: behind; discuss at the Daily Scrum.
Actual below ideal: ahead, or estimates were high.
Flat line: work stuck, often waiting for testing.
14 / 30
Notes: A sprint burndown shows remaining work (usually story points, vertical axis) over the sprint days (horizontal).
- The dashed grey line is the ideal pace; the red line is reality.
- In the example the team was behind around Day 3–4, then caught up. A line that stays flat and then drops off a cliff on the last day usually means stories were tested and closed only at the end.

## Slide 15: Backlog Refinement (an Activity)
PART 2
Break down, clarify and estimate upcoming backlog items
Ongoing activity, not a Scrum event; often 1–2 sessions a sprint
PO explains value; Developers, including QEs, ask and estimate
QE asks of every story: how will we test this?
QE challenges vague words and adds missing edge cases
Output: small, clear, estimated, testable stories
15 / 30
Notes: Refinement used to be called grooming. The Scrum Guide calls it an activity, not an event, so it is not strictly time-boxed. Many teams spend up to about 10% of their capacity on it.
Example: story "As a shopper, I want to search for products so that I find what I need quickly." Ananya asks: what is "quickly"? What happens with no results, a typo, or 1,000 results? Rohan answers; Karan re-estimates from 3 to 5 points; two new acceptance criteria are added.
Common mistakes: a quick "just estimate it" meeting with no testing discussion; refining too far ahead (stories go stale).

## Slide 16: The Scrum Events
Planning, Daily Scrum, Review and Retrospective, inside the Sprint
03
16 / 30
Notes: The Sprint is the container event. Inside it are four events. One slide each: purpose, who, timebox, output and the QE's role.

## Slide 17: Sprint Planning
PART 3
Purpose: agree a Sprint Goal, choose the work for it, and plan how to do it.
Who: the whole Scrum Team.
Timebox: up to 4 h (2-week sprint).
Output: Sprint Goal and Sprint Backlog.
QE ROLE
• Check each story has testable criteria
• Include testing effort in capacity
• Flag risks; add test tasks
17 / 30
Notes: Inputs: refined Product Backlog, Product Goal, Definition of Done, recent velocity, team capacity, last retrospective's actions.
QE also identifies environments, test data, accounts and tools, and leaves time for fixing and retesting.
Common mistakes: over-committing because testing time was not counted; a list of unrelated stories called a goal; starting stories with unclear AC; forgetting leave and holidays.
Example script: Rohan proposes the goal "A shopper can find a product, add it to the cart and see an accurate total." Karan notes capacity of about 26 points. Ananya asks for test data with at least 50 products and suggests taking 24 points to leave room for retesting. The team agrees.

## Slide 18: Daily Scrum
PART 3
Purpose: inspect progress toward the Sprint Goal and plan the next 24 hours.
Who: the Developers, including QEs.
Timebox: 15 min, same time and place.
Output: updated plan; blockers named.
QE ROLE
• Report status by story, not test counts
• Raise blockers early
• Warn when "ready for test" piles up
EXAMPLE
Ananya: "Search: two issues found, one fixed. Today: retest, then add-to-cart. Blocker: stale test data; can we fix it after this?"
18 / 30
Notes: The Scrum Master makes sure it happens and stays within 15 minutes; the PO may listen.
- Details are taken offline afterwards.
- Why the example is good: specific, linked to the goal, names a blocker and asks for help.
Common mistakes: a status report to the Scrum Master or a manager; running 30–45 minutes; problem-solving in the meeting; vague updates ("working on testing"); QEs left out.

## Slide 19: Sprint Review
PART 3
Purpose: inspect the Increment with stakeholders and adapt the Product Backlog.
Who: Scrum Team and key stakeholders, e.g. Sunita.
Timebox: up to 2 h (2-week sprint).
Output: feedback; revised Product Backlog.
QE ROLE
• Demo only work that meets the DoD
• Give an honest view of quality
• Turn feedback into backlog items
19 / 30
Notes: Inputs: the Increment, the Sprint Goal, the Product Backlog, the DoD.
QE also checks the demo environment is stable with realistic data, and rehearses.
Example: Rohan recalls the Sprint Goal; Karan demonstrates search and adding two items to the cart. Ananya explains what was verified (cart totals with discounts on two browsers) and one known low-severity issue. Sunita asks for a "recently viewed" list, which Rohan adds to the backlog.
Common mistakes: slides instead of working software; showing unfinished work; nobody capturing feedback; treating it as an approval meeting.

## Slide 20: Sprint Retrospective
PART 3
Purpose: inspect how the sprint went and commit to concrete improvements.
Who: the Scrum Team only.
Timebox: up to 1.5 h (2-week sprint).
Output: a few improvement actions with owners.
QE ROLE
• Share quality observations with facts
• Stay blame-free
• Own and follow up quality actions
20 / 30
Notes: Rhythm of a good retrospective: set the stage, gather data, generate insights, decide what to do, close.
Blame-free: "the story arrived late", not "Karan was late".
Example: Meera runs Start/Stop/Continue. Ananya points out three of five stories reached testing only on Day 8 or later. The team agrees to split any story over 5 points during refinement and to smoke-check each build before handing it to the QE.
Common mistakes: skipping it when the sprint went well; complaining without actions; too many actions; never reviewing earlier actions.

## Slide 21: Retrospective Formats
PART 3
Format | How it works
Start / Stop / Continue | What to start, stop and keep doing; good first format
4Ls | Liked, Learned, Lacked, Longed for
Mad / Sad / Glad | Notes under feelings; surfaces tension
Sailboat | Wind (helped), anchors (slowed), rocks (risks ahead)
21 / 30
Notes: Change the format every few sprints so the retrospective doesn't become a ritual.
- Whatever the format, finish with a short list of concrete, owned actions; the most important one goes into the next Sprint Backlog so it actually happens.

## Slide 22: Testing Inside a Sprint
Continuous testing, the flow of one story, and what to do when things go wrong
04
22 / 30
Notes: Part 4: the QE's view of the sprint.

## Slide 23: Scrum-Fall vs Continuous Testing
PART 4
Scrum-fall (avoid)
Week 1: developers code
Week 2: QE tests everything
Continuous (aim for)
Story 1: build
test
Story 2: build
test
Story 3: build
test
Story 4: build
test
Story 5: build
test
Split stories small so they reach testing from Day 3
QE writes test scenarios while the developer codes
Developers help test when the testing column fills
23 / 30
Notes: Scrum-fall is a mini-waterfall inside the sprint: the relay race squeezed into two weeks. Stories arrive for testing on Day 8 or 9, defects are found too late to fix, and the goal is missed.
- Continuous testing: each small story is tested as soon as it is built, so defects are fixed the same day or the next.

## Slide 24: The Flow of a Single Story
PART 4
Refined
(AC ready)
Planned
(Day 1)
In Development
In Testing
Fix / Retest
Done
(meets DoD)
Testability questions
Test tasks estimated
QE writes scenarios
Run tests, explore
Confirm fix, regression
Ready for Review
Green: the QE's work at each step. While the developer codes, the QE is already preparing tests.
24 / 30
Notes: Follow one story across the board. The QE is involved before a line of code is written (refinement and planning), prepares scenarios during development, tests the moment code is available, and confirms fixes with regression.
- The dashed red arrow: if a defect is found, the story loops back between testing and fixing until it meets the DoD.

## Slide 25: Healthy vs Unhealthy Testing Rhythm
PART 4
Healthy | Unhealthy
Stories reach testing steadily from Day 3 | Most stories reach testing on Day 8 or 9
QE and developer talk about issues the same day | Issues wait in a queue for days
Regression is small and frequent | Regression is one stressful event at the end
Burndown goes down gradually | Flat burndown, then a cliff
Final hardening takes a day or less | Hardening becomes a multi-day phase
25 / 30
Notes: Use this table as a health check in the retrospective. If the right-hand column sounds familiar, the fix is usually smaller stories and earlier testing, not more overtime.

## Slide 26: When the Sprint Goal Is at Risk
PART 4
Say so early, at the Daily Scrum; don't wait for Day 10
Negotiate scope with the PO, keeping the goal
Swarm on the most important unfinished item
Never lower the Definition of Done to hit a date
Never extend the sprint
Missed goal? Unfinished work returns to the backlog
26 / 30
Notes: The Sprint Goal is the commitment, not every individual story.
- Better less that is Done than more that is not.
- If the goal is still missed: unfinished stories don't count toward velocity, go back to the Product Backlog, and the team discusses why in the retrospective. It is a learning event, not a punishment.

## Slide 27: A Bug Found Late on Day 9
PART 4
Report it now
Assess impact
Decide with the PO
Keep the DoD
Be transparent
Learn in the retro
Tell the team at once
Breaks the goal? Workaround?
Fix now, cut scope, or move back
Serious open bug = not Done
Say what wasn't completed
Why was it found late?
GUIDING PRINCIPLE
Hiding a late bug costs far more than reporting it. Raise it early, calmly and with facts.
27 / 30
Notes: Options in step 3: fix now if time allows and the goal depends on it; reduce the story's scope and ship what is verified; or move the story back to the Product Backlog.
- In the retrospective ask: could better acceptance criteria, earlier testing or more regression have caught it sooner?

## Slide 28: Common Mistakes
PART 4
Estimating stories without any testing discussion
Over-committing because testing time wasn't counted
Daily Scrum as a status report, running 30+ minutes
Demoing unfinished work at the Sprint Review
Retrospectives with complaints but no actions
Testing everything in the last two days of the sprint
28 / 30
Notes: More: excluding QEs from events because "testing is separate"; ignoring blockers; skipping the retrospective when the sprint went well; treating the review as an approval meeting.
- Ask the room which of these they think is most common, and why.

## Slide 29: Key Takeaways
SUMMARY
1
A sprint is a fixed timebox (≤1 month, often 2 weeks) with one goal.
2
Each artifact has a commitment: Product Goal, Sprint Goal, DoD.
3
Stories describe value; Given/When/Then criteria become tests.
4
Points size work; velocity forecasts; burndown shows progress.
5
The QE contributes in every event, and in refinement.
6
Testing is continuous inside the sprint, never a final phase.
29 / 30
Notes: Next: Agile roles, who does what on the team, and where the QE fits. Then Jira, the tool that runs all of this.

## Slide 30: Additional Resources
1
The Scrum Guide (2020 edition)
https://scrumguides.org/scrum-guide.html
2
Atlassian Agile Coach: Scrum
https://www.atlassian.com/agile/scrum
3
Scrum.org Resources
https://www.scrum.org/resources
30 / 30
Notes: The Scrum Guide is about 13 pages; ask learners to read it before the end of the week.