## Slide 1: Test Planning and Test Execution
WEEK 3 · TUESDAY
Deciding what, how, by whom and when to test, then running the tests, recording the truth and reporting it.
Test plan
Risk
Estimation
Test cases
Execution
Reporting
Notes: This deck covers STLC phases 2 to 6 at core depth: plan, design cases, run, report, close.
Requirements analysis (previous deck) fed us clarified requirements and an RTM.
The sample plan, test cases and execution log are built live in the demo and exercise, not on slides.
One analogy runs through the deck: a trip itinerary.

## Slide 2: Learning Objectives
1
Explain what a test plan contains and how it differs from a strategy.
2
Prioritise testing with a risk matrix and estimate the effort.
3
Write test cases with standard fields; group them into suites and cycles.
4
Execute tests, record statuses and evidence, and handle blocked tests.
5
Track progress with execution metrics and write status and closure reports.
Test Planning and Execution · Week 3 · Tuesday | 2 / 32
Notes: Five objectives, five parts.
Interview link: 'Can you write a test plan and test cases, and how do you report progress?'
Boundaries: defect reports are the next deck; test design techniques Thursday; testing principles Wednesday; regression Friday.

## Slide 3: Test Planning
What a plan answers, strategy versus plan, plan anatomy and the Agile one-pager
01
Test Planning and Execution · Week 3 · Tuesday | 3 / 32
Notes: Part 1: why we plan and what goes in the plan.
This part has 5 concept slides, about 10 minutes.
Before starting, recap the previous part in one sentence and ask one check question.

## Slide 4: What Test Planning Answers
PART 1
Test plan
objectives and approach within constraints
What?
scope in and out
Why?
objective
How?
approach, levels, types
Who?
roles
When?
schedule, milestones
Where?
environments, data
What if?
risks, suspension
Done?
exit criteria
Like a trip itinerary: destination, route, people, times, plan B, and when the trip is over.
Test Planning and Execution · Week 3 · Tuesday | 4 / 32
Notes: Definition: defining the objectives of testing and the approach for meeting them within time, people, budget, tools and environments.
Purposes: align the team, reduce risk, control effort, define done, communicate, and leave an audit trail in regulated industries.
A plan is a living document: update it when reality changes. 'Plans are useless, but planning is indispensable.'
This is the deck's one analogy; use it again for execution (taking the trip and noting what happened at each stop).

## Slide 5: Test Strategy vs Test Plan
PART 1
Test strategy
Organisation level · long-lived · owned by the QE lead or head of quality
Plan: Release 1.2
project level · changes often
Plan: Login feature
project level · changes often
Plan: Sprint 7
project level · changes often
 | Strategy says | Plan says
Example | Web products are tested on the latest two Chrome and Firefox versions. | Login is tested on Chrome and Firefox, 3 to 14 March, by Ananya.
Test Planning and Execution · Week 3 · Tuesday | 5 / 32
Notes: Strategy: 'In general, how do we test here?' Rarely changes; reused across projects. Content: principles, test levels used, tool standards, defect management, metrics, automation approach.
Plan: 'For this release, what exactly, who, and by when?' Specific scope, schedule, resources, environments, risks, criteria.
Small teams may merge the two or quote a few strategy rules inside the plan; what matters is the difference in level.
Trip version: strategy is the company travel policy; the plan is the itinerary for one trip.

## Slide 6: Anatomy of a Test Plan
PART 1
What and why
• Identifier, objective
• Scope in / out
• Items and features
How
• Approach
• Levels and types
• Environment, test data
Who and when
• Roles
• Schedule, milestones
• Estimate, resources
Control
• Entry / exit / suspension
• Risks, assumptions
• Deliverables, approvals
EXAMPLE CRITERIA
Exit: all planned cases run; 95%+ passed; no open Critical or High defects; report approved.
Suspend if the smoke test fails; resume when a new build passes it.
Test Planning and Execution · Week 3 · Tuesday | 6 / 32
Notes: Standards: IEEE 829 and ISO/IEC/IEEE 29119-3 define plan outlines; learners need the sections, not clause numbers.
The out-of-scope list protects you: social login, performance, third-party internals.
Entry, exit, suspension and resumption criteria were introduced on Monday; here they get concrete values.
Assumption: believed true but unconfirmed ('QA environment will be stable'). Dependency: something another team provides ('email service configured').

## Slide 7: Test Levels and Test Types
PART 1
Acceptance (UAT)
business users, PO
System
QE team
Integration
developers and QE
Unit
developers
LEVELS: where in the build-up we test
TYPES
Functional
Non-functional
Regression
Smoke and sanity
Types say what quality we check, at any level.
Test Planning and Execution · Week 3 · Tuesday | 7 / 32
Notes: Levels were named in Monday's V-Model; here we decide which ones the plan covers.
Unit: a password-length function. Integration: form saves to the database and calls the email service. System: register, verify, log in, lock out, log out through the UI. Acceptance: PO confirms a new customer can sign up in under two minutes.
Types: functional (does it), non-functional (how well), regression (did a change break something, Friday), smoke and sanity (later in this deck).
A typical plan focuses on system-level functional testing and relies on developers' unit and integration tests.

## Slide 8: The One-Page Agile Test Plan
PART 1
▸ Goal
▸ Scope in / out
▸ Approach and risk focus
▸ Environment and data
▸ Roles
▸ Key dates in the sprint
▸ Entry and exit (DoR / DoD)
▸ Top 3 to 5 risks
▸ Reporting
Just enough planning: nobody reads 30 pages in a 2-week sprint.
The Definition of Done often acts as exit criteria.
Test tasks appear as sub-tasks on the story.
Large, regulated or multi-team work still needs a full plan.
Test Planning and Execution · Week 3 · Tuesday | 8 / 32
Notes: Agile values working software over comprehensive documentation: that means just enough planning, not no plan.
Planning happens in sprint planning, progress at the daily scrum, results at review and retrospective (Monday's Scrum deck).
Many organisations use a master test plan for the release plus a one-pager per sprint or feature.
The exercise asks learners to write a one-page plan for a login feature.

## Slide 9: Risk and Estimation
Deciding what to test first, and how long it will take
02
Test Planning and Execution · Week 3 · Tuesday | 9 / 32
Notes: Part 2: we can never test everything, so we prioritise and estimate.
This part has 3 concept slides, about 6 minutes.
Before starting, recap the previous part in one sentence and ask one check question.

## Slide 10: Risk-Based Testing: The Risk Matrix
PART 2
Risk score = Likelihood × Impact (1 low, 2 medium, 3 high). Test the highest first and deepest.
Likelihood 3
3
6
9
Likelihood 2
2
4
6
Likelihood 1
1
2
3
Impact 1
Impact 2
Impact 3
Feature area | L | I | Score
Account lockout | 3 | 3 | 9
Password rules | 3 | 2 | 6
Duplicate email | 2 | 3 | 6
Small-phone layout | 2 | 1 | 2
Email wording | 1 | 1 | 1
Red 6-9: earliest, deepest · Orange 3-4: normal · Grey 1-2: light or last
Test Planning and Execution · Week 3 · Tuesday | 10 / 32
Notes: Exhaustive testing is impossible (testing principles, Wednesday), so prioritise by risk.
Likelihood rises with complex code, new technology, frequent change. Impact: lost money or data, security, legal trouble, angry customers.
Ratings are judgments: agree them with developers (Karan) and the PO (Rohan).
The manager question: 'We only have two days left. What do you test?' Answer: the red cells.

## Slide 11: Estimating Test Effort
PART 2
Work breakdown
Split into small tasks, estimate each, add up.
Best when: Scope is known
Three-point (PERT)
Optimistic, most likely, pessimistic.
Best when: Uncertainty is high
Experience-based
Past projects and expert judgement.
Best when: Similar work exists
Story points
Relative size; testing included (recap).
Best when: Agile team with velocity
RULE
Always add a buffer (10-20%) and state assumptions: "assuming a stable environment and 8 builds or fewer".
Test Planning and Execution · Week 3 · Tuesday | 11 / 32
Notes: Estimation predicts effort (person-hours) and duration (calendar time). Always uncertain; give reasons.
Experience-based has a structured form: Wideband Delphi, where experts estimate independently, discuss and re-estimate.
Story points, velocity and planning poker were taught on Monday; a tester's voice in planning poker matters because test effort is often forgotten.
Weaknesses: WBS forgets tasks; PERT relies on honest guesses; experience is imperfect; points need team history.

## Slide 12: WBS and PERT in Practice
PART 2
Task (login and registration) | Hours
Review requirements, write conditions | 6
Write and review 40 test cases | 14
Data, environment, smoke tests | 5
Execute cycle 1, log defects | 12
Retest, regression, reports, closure | 11
Total (≈ 8 person-days) | 48
E = (O + 4M + P) / 6
O = 2, M = 4, P = 9 days
E = (2 + 16 + 9) / 6 = 4.5 days
SD = (P − O) / 6 ≈ 1.2 days
Commit to about 5.5 to 6 days.
Test Planning and Execution · Week 3 · Tuesday | 12 / 32
Notes: WBS conversion: 48 hours at 6 productive hours a day = 8 person-days; with two testers about 4 calendar days plus a buffer.
PERT: the pessimistic value pulls the average above the most-likely 4 days; things usually take longer than we hope.
Say it like this: 'About 4.5 days, give or take just over one day. I'd commit to 5.5 to 6.'
Cross-check one technique with another when the stakes are high.

## Slide 13: Test Cases
Fields, good and poor cases, and how cases are grouped for execution
03
Test Planning and Execution · Week 3 · Tuesday | 13 / 32
Notes: Part 3: the test case is one checklist line on the itinerary.
This part has 4 concept slides, about 8 minutes.
Before starting, recap the previous part in one sentence and ask one check question.

## Slide 14: Anatomy of a Test Case
PART 3
Written before execution
ID
TC-LOG-001
Title
Login succeeds with valid credentials
Requirement
REQ-LOGIN-01
Preconditions
User exists, verified, not locked
Steps
Open login · enter email · password · Log in
Test data
user01@example.com / Secure#2024
Expected result
Dashboard shows "Welcome"; Log out visible
Priority
High (from risk)
Filled during execution
Actual result
Status
Build, date, tester
Defect link
Postcondition: the state after the test, e.g. one new user record.
Test Planning and Execution · Week 3 · Tuesday | 14 / 32
Notes: Why write cases instead of clicking around: repeatability, coverage, training, evidence, regression.
Clicking without a script is exploratory testing (Friday): valuable, complements but does not replace planned cases.
Precondition = state before step 1; test data = exact values; postcondition = state afterwards.
Optional fields: author, environment, type (positive or negative), automation status.

## Slide 15: Poor vs Good Test Case
PART 3
Poor
ID: 1
Title: Test login
Steps: Try to log in
Expected: It works
Good
TC-LOG-001 · REQ-LOGIN-01 · High
Pre: user01 exists, verified, not locked; logged out
Steps: open Login · enter email · enter password · click Log in
Expected: Dashboard; header "Welcome, User One"; Log out link
Poor: vague title, no data, no start point, "it works" cannot be verified. Two testers would disagree.
Test Planning and Execution · Week 3 · Tuesday | 15 / 32
Notes: Ask learners to list everything missing from the poor case before showing the critique.
Good case: one purpose, explicit data, observable expected result, requirement link, priority.
Test data uses example.com addresses, never real people.
Thursday's techniques choose which inputs to test; today is about writing them clearly.

## Slide 16: Qualities of a Good Test Case
PART 3
One purpose
If five checks fail together, which broke?
Precise steps
Any teammate can follow without guessing
Observable result
URL, message text, saved data; never 'works properly'
Independent
No hidden dependence on another case
Traceable
Linked to a requirement and a priority
Positive and negative
Invalid input handled safely, no crash
Test Planning and Execution · Week 3 · Tuesday | 16 / 32
Notes: Also: short and maintainable; avoid 30-step monsters.
Dependent cases are allowed only when stated in the preconditions.
Negative tests check the system rejects bad input with a clear message, no crash and no corrupted data; positive and negative testing is Wednesday.
Exercise: rewrite three poor cases from the exercise starter file.

## Slide 17: Test Suites and Test Cycles
PART 3
Test case repository
written once
Registration suite
Login suite
Smoke suite
Cycle 1
build 1.0.3 · Mon-Wed
Cycle 2
build 1.0.4 · retest + regression
Suite: cases grouped for a purpose (a playlist). Cycle: one round of execution on one build; each case gets a result per cycle.
Test Planning and Execution · Week 3 · Tuesday | 17 / 32
Notes: One case can belong to several suites: a login case can be in Login, Smoke and Regression.
Cycle (test run): Cycle 1 runs all cases on the first accepted build; after fixes, Cycle 2 retests and runs regression.
Tools: Jira plus a test-management add-on (Xray, Zephyr) or TestRail store cases once and create an execution per cycle.
Without a tool: a spreadsheet with one results column per cycle.

## Slide 18: Test Execution
Readiness, smoke tests, the execution routine, statuses and retesting
04
Test Planning and Execution · Week 3 · Tuesday | 18 / 32
Notes: Part 4: taking the trip and writing down what happened at each stop.
This part has 5 concept slides, about 10 minutes.
Before starting, recap the previous part in one sentence and ask one check question.

## Slide 19: Ready to Execute?
PART 4
✓
Requirements baselined
✓
Cases reviewed and approved
✓
Build deployed, version known
✓
Test data loaded
✓
Access and tools ready
✓
Environment checked (email inbox, config)
Smoke test passed?
Start execution
Reject build, report at once
Record build, browser, OS and date on every run.
Test Planning and Execution · Week 3 · Tuesday | 19 / 32
Notes: Confirm the plan's entry criteria before running a single test; report any 'No' to the test lead immediately.
A shaky environment produces false failures: tests fail because the environment is wrong, not the software.
Environment checklist: correct build in the footer, database seeded, test mailbox, browsers, URLs, configuration such as lockout values, logs readable.
Vikram (DevOps) owns environment fixes; Ananya raises a ticket with evidence.

## Slide 20: Smoke vs Sanity
PART 4
Smoke: broad and shallow
Every new build, 15-30 minutes
Is the build testable at all?
Outcome: accept or reject
Sanity: narrow and deeper
After a small fix or change
Does this change behave sensibly?
Outcome: proceed or send back
EXAMPLE
Smoke: site loads · Registration opens · Login opens · test user reaches Dashboard · Log out works. Any failure: build rejected.
Test Planning and Execution · Week 3 · Tuesday | 20 / 32
Notes: Smoke comes from hardware: switch on the new board; if smoke comes out, stop.
Sanity example: after a fix to the password error message, check that message and the surrounding form.
Teams use the two words loosely; learn the idea and check your team's meaning.
Smoke suites are often scripted and automated; sanity checks are often quick and unscripted.

## Slide 21: The Execution Routine
PART 4
1. Pick next case (highest risk first)
2. Set up preconditions
3. Follow steps exactly
4. Compare actual with expected
5. Record status and evidence
6. Fail? Log and link a defect
EVIDENCE
Evidence: screenshot with URL bar, short video, console or log lines, exact data, build. Name files TC-REG-003_short-password.png.
Test Planning and Execution · Week 3 · Tuesday | 21 / 32
Notes: Do not 'improve' steps mid-run; finish what you can and raise a correction.
Record what you saw, not what you assumed. A failed test is good news: a problem found before the customer.
Never mark Pass because you are in a hurry, or Fail because you dislike the design.
For a failure: retry once, search for duplicates, log the defect (next deck) and link it: 'Failed - DEMO-101'. Mask personal data in evidence.

## Slide 22: Five Test Statuses
PART 4
Not Run
attempt
Pass
Fail
Blocked
Skipped
by decision, with a reason
Pass: every check matched
Fail: ran it; behaviour was wrong
Blocked: could not reach the check
Skipped: deliberately not run this cycle
EXAMPLE
Lockout case cannot run: QA lockout threshold is 50, not 5. That is Blocked, not Fail.
Test Planning and Execution · Week 3 · Tuesday | 22 / 32
Notes: Mixing up Blocked and Fail distorts metrics and hides the true picture.
Not Run is also called Not Executed, Unexecuted or To Do.
Use only statuses your team has agreed; some tools add In Progress.
Blocked example 2: login cannot be tested because registration fails.

## Slide 23: Retesting vs Regression
PART 4
Fix in build 1.0.4
Retesting (confirmation)
Re-run the exact case that failed.
"Is the broken thing fixed?"
Regression
Re-run related cases that passed before.
"Did the fix break anything else?"
Reserve time for both in every cycle. Regression strategy and automation: Friday.
Test Planning and Execution · Week 3 · Tuesday | 23 / 32
Notes: Retesting is predictable: exactly the failed cases. Regression is selected by risk and impact, often automated.
Timing: retest after the defect is fixed; regression after any change (fix, feature, configuration).
The defect deck adds the retest checklist used before closing a bug.
Friday owns regression testing; today we only plan time for it.

## Slide 24: Tracking, Reporting and Closure
Progress, execution metrics, status reports, blockers and the closure report
05
Test Planning and Execution · Week 3 · Tuesday | 24 / 32
Notes: Part 5: telling the truth about where testing stands.
This part has 5 concept slides, about 10 minutes.
Before starting, recap the previous part in one sentence and ask one check question.

## Slide 25: Tracking Progress Daily
PART 5
Chart: Test cases
| Day 1 | Day 2 | Day 3 | Day 4
Planned executed | 10 | 20 | 30 | 40
Actual executed | 8 | 15 | 30 | 36
Update status as you finish each case, not at day end.
Compare actual with plan every day.
Planned 10 a day, doing 6? Raise it early.
Test Planning and Execution · Week 3 · Tuesday | 25 / 32
Notes: An execution burn-up: 'tests executed' should rise toward the total.
Track tests planned, executed, passed, failed, blocked, skipped, not run; defects found, open, fixed; effort spent versus planned.
Day 2 here is behind plan; Day 3 caught up after a blocker was removed.
Dashboards show the truth only if statuses are updated as you go.

## Slide 26: Execution Metrics
PART 5
Execution %
executed ÷ planned × 100
Pass %
passed ÷ executed × 100
Planned | Passed | Failed | Blocked + skipped + not run
120 | 90 | 12 | 18
Executed = 102 → Execution 85% · Pass 88.2%
READ THE NUMBERS
"The pass rate looks healthy, but 18 tests give us no information yet, so I cannot recommend release."
Test Planning and Execution · Week 3 · Tuesday | 26 / 32
Notes: Executed usually means Pass or Fail; Blocked, Skipped and Not Run are not executed.
Some teams divide passes by total planned (90/120 = 75%); state your definition in the plan.
Defect metrics (density, leakage, DDP) belong to the defect lifecycle deck, next.
Vanity metrics: lots of cases run or bugs found is not automatically good. Never reward testers by bug count.

## Slide 27: The Daily Status Report
PART 5
AMBER
Day 3 of 4 · build 1.0.3
Progress
40 planned · 30 run · 26 pass · 4 fail · 2 blocked
Defects
2 new · 5 open (2 High)
Blockers
Lockout threshold is 50 in QA
Risk
Top security tests may slip
Help needed
Vikram: fix setting by Thu 10:00
Brief, factual, honest.
Green / Amber / Red overall status.
A request for action, not a diary: who, what, by when.
Test Planning and Execution · Week 3 · Tuesday | 27 / 32
Notes: Contents: period and build, planned versus executed, results, new defects, blockers, risks, plan for tomorrow, help needed.
Builds trust: no surprises at the end of the cycle.
The full template is in the written lesson and the exercise templates folder.
Prepared by Ananya; sent to Rohan, Meera, Karan and Vikram.

## Slide 28: Blocked Tests and Schedule Slips
PART 5
Blocked test
Schedule slipping
1. Confirm it is truly blocked
1. Detect early: plan vs actual daily
2. Record cause, owner, ticket ID
2. Report honestly with a new date
3. Escalate the same day
3. Re-prioritise by risk
4. Run unblocked tests meanwhile
4. Offer options; others decide
5. Many blocked? Check suspension
5. Never mark tests passed unrun
Test Planning and Execution · Week 3 · Tuesday | 28 / 32
Notes: Blocked: idle time is the enemy; reorder work, and retest blocked cases as soon as the block is removed.
Slippage options: add a tester, reduce scope with PO agreement, extend the date, parallelise, accept a stated risk.
Example wording: 'At the current rate we finish on 12 March instead of 10 March.'
Update the plan and risk list, and bring the lesson to the retrospective.

## Slide 29: The Test Closure Report
PART 5
Exit criteria check
✓
100% of planned tests executed
✓
Pass rate at least 95%
✓
No open Critical or High defects
✓
Medium defects fixed or deferral approved
✓
Every requirement has an executed test
Recommendation
Release, subject to the PO accepting the listed risks.
The report recommends; the business decides.
Also: archive cases, data and results; hold a lessons-learned session; get sign-off.
Test Planning and Execution · Week 3 · Tuesday | 29 / 32
Notes: Test closure: verify exit criteria, finish documents, archive, learn lessons.
The closure (summary or exit) report says what was tested, what was found, what remains, and the recommendation.
Typical sections: execution summary, defect summary, exit criteria check, open risks, recommendation.
Rohan (PO) and Sunita (business owner) make the release call using this report.

## Slide 30: Common Mistakes
COMMON MISTAKES
Mistake | Do instead
No out-of-scope list in the plan | State what will not be tested
Testing in random order | Test the highest risk first
Estimates with no buffer or assumptions | Add 10-20% and state assumptions
Vague expected results ('works properly') | Write observable results
Marking Blocked tests as Fail | Use Blocked, with cause and owner
Reporting only the pass rate | Show blocked and not-run tests too
Test Planning and Execution · Week 3 · Tuesday | 30 / 32
Notes: Others: updating statuses only at day end; hiding a slipping schedule; treating the plan as a one-time document.
Roles across planning and execution (written lesson): QE writes and runs cases; QE lead owns the plan; developers fix and deploy; PO decides defect priority and release.
Ask learners which mistake costs the most if found late.

## Slide 31: Key Takeaways
SUMMARY
1
A plan answers what, why, how, who, when and what if; a strategy sits above it.
2
Risk = likelihood × impact decides the order and depth of testing.
3
Estimate with WBS, PERT, experience or points; add a buffer and assumptions.
4
Good test cases are precise, observable, traceable; suites group them, cycles run them.
5
Check readiness and smoke first; record Pass, Fail, Blocked, Skipped honestly with evidence.
6
Report daily and close with facts and a recommendation; the business decides.
Test Planning and Execution · Week 3 · Tuesday | 31 / 32
Notes: Quick check: 'What is the difference between Blocked and Fail?'
Bridge: every failed test becomes a defect; the next deck follows it through its lifecycle.
Give learners one minute to write the takeaway they found most useful; take two or three answers.

## Slide 32: Additional Resources
1
ISTQB Foundation Level syllabus
https://www.istqb.org
2
ISTQB Glossary
https://glossary.istqb.org
3
Guru99: Test Plan: What is, How to Create (with Example)
https://www.guru99.com/test-planning.html
4
Guru99: How to Write Test Cases: Sample Template with Examples
https://www.guru99.com/test-case.html
Test Planning and Execution · Week 3 · Tuesday | 32 / 32
Notes: The written lesson contains the full sample plan, test cases and execution log for a login feature.
Resources are for self-study after class; none are needed for today's exercise.
The written lesson for this topic is the full reference; slides are the presentation layer.